## Sheet1
topic_name | topic_description
Meeting Info | **Meeting Summary** **Date:** [Not specified] **Participants:** Aaron, Andy L, Andy S, Arnav, Chi, Fairy, Karen
### 1. Main Topics Discussed | - **AI@DSCubed Website Redesign** - **Discord Bot Enhancement** - **Committee Management System**
### 2. Key Decisions Made | - The Website Redesign wireframes are complete; development phase to begin imminently. - React with Next.js confirmed as the preferred tech stack for the Website Redesign. - Implementation of breadcrumb navigation system agreed for improved website navigation. - Mobile usability for the Website Redesign requires further adjustments; a comprehensive accessibility audit will be conducted. - Discord Bot meeting scheduling functionality nearly complete; notification system well-received though settings need clarity enhancements. - Advanced search filters to be added to the Discord Bot’s project tracking feature. - Bug fixes prioritized for Discord Bot reminders and Committee Management System duplicate user records. - Database query optimization and caching strategies progressing for the Committee Management System. - User permissions review underway to ensure proper access controls. - A shared UI component library to be established to maintain consistent design patterns across projects. - User survey will be conducted to gather feedback on Website Redesign color scheme and overall usability.
### 3. Action Items / Next Steps | **AI@DSCubed Website Redesign** - Arnav: Finalize tech stack and coordinate CMS integration; implement breadcrumb navigation; coordinate with DevOps on CDN integration; collaborate with Fairy to contact UX team for error handling improvements. - Chi: Conduct accessibility audit focusing on mobile responsiveness; liaise with Karen and design team on responsive breakpoints. - Fairy: Contact UX team for best practices on user feedback and error handling. - Karen: Confirm responsive design breakpoints and finalize color scheme survey distribution. **Discord Bot Enhancement** - Andy L: Complete bug fixes on meeting reminders; draft content for project milestones timeline; test automated workflows; write data validation scripts; ensure performance optimization roadmap. - Andy S: Finish calendar integration; enhance notification settings with added tooltips; initiate timeline feature development. - Aaron: Refine notification settings; review system integration points; prepare rollback plan. - Chi: Suggest adding export functionality to backlog; monitor user feedback on UI/UX. **Committee Management System** - Andy S: Optimize database queries; set up monitoring and alerts for system performance; automate user onboarding; review user roles/permissions. - Arnav: Implement unique constraints to prevent duplicate records; finalize database schema; coordinate with DevOps for caching/CDN; explore Slack integration for performance alerts. - Andy L: Write scripts for data integrity validation; test automated workflows.
### 4. Relevant Projects Connected to Discussions | - **AI@DSCubed Website Redesign:** UX improvements, tech stack finalization, navigation restructuring, CMS integration, responsive/mobile design. - **Discord Bot Enhancement:** Meeting scheduling, notifications, accessibility, new timeline feature, project tracking improvements. - **Committee Management System:** Database performance, user permissions, onboarding automation, data integrity, monitoring.
### 5. Participant Contributions | - **Aaron:** Project oversight, bug identification, rollback planning, action item summarization. - **Andy S:** Website development lead, analytics dashboard optimization, Discord Bot calendar and notification improvements, Committee Management System query optimization. - **Andy L:** Discord Bot feature development, Committee Management System testing and automation, content drafting. - **Arnav:** Technology stack research and implementation lead, database schema and constraints, DevOps coordination, UX improvements coordination. - **Chi:** Accessibility and usability auditing, UI feedback, suggesting monitoring enhancements and features backlog. - **Fairy:** UX liaison for Website Redesign error handling and feedback. - **Karen:** Design team coordination on responsive breakpoints and color scheme.
### 6. Deadlines and Milestones | - Development phase for Website Redesign to commence soon following wireframe approval. - Accessibility audit and mobile testing scheduled ahead of mobile version release. - Follow-up meetings for each project scheduled next week to review progress and next steps. - User survey on Website redesign color scheme and usability to be distributed promptly.
**Summary Conclusion:** | The meeting efficiently covered substantial progress and upcoming priorities across three key projects—AI@DSCubed Website Redesign, Discord Bot Enhancement, and Committee Management System. Clear action items were assigned with an emphasis on user experience, technical robustness, and design consistency. The team emphasized cross-project collaboration, particularly the establishment of a shared component library to unify design standards. Upcoming deadlines focus on transitioning designs into development, accessibility validation, and enhanced system monitoring. Follow-up meetings are set to ensure accountability and sustained momentum.